## Red Flag Tracker
PROJECT RIDGELINE — DILIGENCE RED FLAG TRACKER
Ridgeline Environmental Services, Inc. ¦ Sycamore Capital Partners, LP ¦ December 2024 ¦ CONFIDENTIAL
RF # | Category | Red Flag Title | Severity | Source Document(s) | Detailed Finding | Est. Financial Exposure | Probability | Accrual / Reserve | Status | Required Action | Owner | Due Date | Notes
RF-14 | Customer / Contract | DOE IDIQ Ceiling Exhaustion — $12.1M FY2025 Revenue Headwind | CRITICAL | customer-contract-summary.xlsx (DOE IDIQ tab); CIM §VI.D; QoE Revenue tab | IDIQ Contract DE-EM-0005523 has $45.0M ceiling; $32.7M consumed (72.7%) in 61.7% of contract period. Remaining ceiling: $12.3M. At TTM run rate of $24.4M/yr, ceiling exhausted ~April–May 2025. Contract expires Aug 31, 2026 — 16 months of unfunded period. Contract non-assignable per Anti-Assignment Act; Clause H-12 requires 30-day ownership change notification. | $12.1M revenue headwind; $15–25M EV impact at 8–9x | Probable (ceiling exhaustion) | $0 | Open | Engage DOE Contracting Officer re: ceiling modification. Adjust valuation model for downside scenario. Make DOE continuity a closing condition. | Deal Team / Legal | Pre-Signing | Not disclosed in CIM. Critical valuation risk.
RF-01 | Financial / QoE | EBITDA Discrepancy: CIM ($22.8M) vs. QoE Data Room ($23.8M) — $1.0M Gap Unresolved | HIGH | CIM §VI.B; qoe-data-request-response.xlsx (EBITDA Bridge tab) | CIM states Adjusted EBITDA of $22.8M. QoE EBITDA Bridge calculates $23.8M. Management acknowledges the $1.0M gap but states 'the specific adjustment category causing the discrepancy has not been identified.' At 8–9x multiple, this implies $8–9M EV swing. Valuation cannot be finalized until reconciled. | $8–9M enterprise value impact | Certain (discrepancy exists) | N/A | Open | Demand written reconciliation before LOI finalization. Confirm which figure is the QoE starting point. | CFO / Bridgewater Forsyth | Immediate | Fundamental data integrity issue.
RF-02 | Financial / QoE | Aggressive EBITDA Add-Backs — $5.4M Total; $4.9M Non-Qualifying Under Bank Definition | HIGH | CIM §VI.B; qoe-data-request-response.xlsx (EBITDA Bridge); credit-agreement-summary.docx §4 | Five add-back categories total $5.4M. Bank's Consolidated EBITDA definition expressly excludes: litigation settlements, owner comp normalization, ERP costs, integration costs, and wind-down costs — capping qualifying non-recurring items at $500K/yr. Bank EBITDA = $18.4M. Litigation settlement add-back is a receipt (not a cost), which is non-standard. Owner comp normalization assumes founders replaced at $400K each — not confirmed post-closing. | $5.4M EBITDA at risk; $43–49M EV impact if fully disallowed | Reasonably Possible (partial disallowance) | N/A | Open | Independently validate each add-back. Confirm post-closing founder compensation. Negotiate EBITDA definition in SPA. | Bridgewater Forsyth / Legal | Pre-Signing | Owner comp normalization is most sensitive item.
RF-06 | Environmental | Grand Junction Phase II ESA — Stale 5+ Years; Unresolved Contamination & Vapor Intrusion Risk | HIGH | phase-ii-esa-executive-summary.docx; environmental-permit-schedule.docx §2.1; real-property-lease-schedule.docx §2.1 | Phase II ESA (June 2019) identified: (1) Petroleum hydrocarbons (TPH-diesel 4,200 mg/kg; benzene in GW at 12 µg/L vs. 5 µg/L standard); (2) Chlorinated solvents (PCE 18 mg/kg soil; PCE 22 µg/L GW; TCE 8.7 µg/L GW — both exceeding CO standards); (3) Vapor intrusion risk in occupied maintenance building (PCE 450 µg/m³ vs. 240 µg/m³ RSL). ESA recommended off-site sentinel wells, vapor intrusion assessment, and periodic re-assessment before any transaction — none completed. 2019 cost estimate ($1.8–2.6M) excludes vapor intrusion mitigation, off-site remediation, and NRD claims. | $2.6M–$10M+ (updated estimate required); excludes off-site and NRD | Probable (remediation required) | $2.2M accrued (stale 2019 basis) | Open | Commission updated Phase II ESA and vapor intrusion assessment immediately. Do not close without current data. Negotiate specific environmental indemnity with higher cap. | Environmental Counsel / Elkhorn | Immediate | ESA explicitly warns against reliance in property transactions without update.
RF-11 | Debt / Change-of-Control | Credit Agreement Change-of-Control — Mandatory $39.2M+ Prepayment Within 5 Business Days | HIGH | credit-agreement-summary.docx §8–9; executed-loi.docx §4(b) | Proposed 100% stock acquisition triggers Change of Control under credit agreement (clauses (a) and (c)). Mandatory prepayment of all obligations within 5 business days: $12.4M revolver + $26.3M term loan + 1.0% prepayment premium (~$263K) + accrued interest (~$200–300K) = ~$39.2–39.3M. No consent/waiver mechanism exists. LOI Net Debt adjustment captures principal but may not include prepayment premium and breakage costs. | $39.2–39.3M (known, quantified closing cost) | Certain | N/A (to be paid at closing) | In Progress | Confirm prepayment premium based on actual closing date. Ensure SPA Net Debt definition includes premium and breakage. Arrange committed refinancing before signing. | Legal / Finance | Pre-Signing | Well-understood but must be precisely quantified in closing mechanics.
RF-18 | Real Property | Salt Lake City Lease — Dual Consent Failure; $16.2M Revenue at Risk | HIGH | real-property-lease-schedule.docx §4.1; litigation-regulatory-summary.docx §V.B; customer-contract-summary.xlsx | SLC lease (Wasatch Industrial Properties) requires prior written consent for any change of control. (1) Pinnacle-to-RES assignment requested April 12, 2022 — no consent received after 32 months. (2) Sycamore acquisition = second change-of-control event requiring separate consent. (3) Landlord sent inquiry letter November 2024 referencing consent clause. (4) Facility serves ~$16.2M annual revenue. (5) Facility also operates under permit still in Pinnacle's name (UTH-0441). Potential pre-existing default condition. | $16.2M revenue at risk; lease termination risk | Reasonably Possible (landlord action) | N/A | Open | Obtain landlord consent to both 2022 assignment and Sycamore transaction before closing. Non-negotiable closing condition. Engage Wasatch Industrial Properties immediately. | Legal / Real Estate Counsel | Immediate | Landlord's November 2024 inquiry suggests awareness and potential leverage.
RF-03 | Financial / QoE | Reported EBITDA Declined 27% YoY in FY2024 Despite 11% Revenue Growth | MEDIUM-HIGH | qoe-data-request-response.xlsx (Historical P&L tab) | FY2024 Reported EBITDA (per QoE P&L) declined from $25.2M (FY2023) to $18.4M (FY2024) — a 27% YoY decline — while revenue grew 11.1%. This margin compression is masked by $5.4M in add-backs. Underlying business generated significantly less cash earnings in FY2024 than FY2023. EBIT margin compressed from 16.0% to 14.5%. Drivers not fully explained in data room. | Structural margin risk; potential $3–5M normalized EBITDA reduction | Reasonably Possible | N/A | Open | Obtain detailed FY2023-to-FY2024 EBITDA bridge. Assess whether margin compression is temporary or structural. | Bridgewater Forsyth | Pre-Signing | Revenue growth with EBITDA decline is a significant quality-of-earnings concern.
RF-04 | Financial / QoE | Fleet Capex Backlog — 44.7% of Fleet Past Useful Life; ~$9.8M Deferred Replacement | MEDIUM-HIGH | qoe-data-request-response.xlsx (Fleet & Equipment Schedule tab; Capex Detail tab) | 38 of 85 fleet assets (44.7%) are at or past stated useful life. Average fleet age 8.2 years vs. 7.0-year useful life. Estimated replacement cost for past-useful-life units: $9.8M. Many marked 'Replacement Deferred' or 'At End of Life — No Replacement Scheduled.' Management's normalized maintenance capex of $4.0–4.5M/yr appears understated. Spreading $9.8M backlog over 3 years implies ~$3.3M/yr catch-up capex. True normalized maintenance capex may be $7.0–7.5M/yr. | $9.8M deferred replacement; $3M+/yr normalized capex understatement | Probable (replacement required) | N/A | Open | Commission independent fleet condition assessment. Adjust normalized maintenance capex in valuation model. Negotiate purchase price reduction or capex true-up. | Operations / Technical Advisor | Pre-Signing | Capex understatement directly inflates free cash flow and valuation.
RF-07 | Environmental | Active CDPHE RCRA Enforcement Action — Penalty Exposure $200K–$1.16M | MEDIUM-HIGH | litigation-regulatory-summary.docx §III.A; environmental-permit-schedule.docx §2.1; executed-loi.docx §5.5 | CDPHE Notice of Violation (Docket CDPHE-HW-2024-0093, July 18, 2024) alleges improper storage of ~14,000 gallons F001/F002 hazardous waste at Grand Junction. Dispute on violation period: RES claims 12 days (max $450K); CDPHE claims 31 days (max $1.16M). No accrual recorded. Settlement conference expected Q1 2025 — potentially concurrent with target signing date. Active RCRA enforcement against primary permitted facility. | $200K–$1.16M penalty; permit standing risk | Probable (some penalty) | $0 accrued | Open | Require resolution or specific indemnity escrow before closing. Obtain CDPHE's current settlement position. Confirm no permit modification risk. | Environmental Counsel | Pre-Signing | LOI §5.5 specifically calls out this matter for special indemnification treatment.
RF-09 | Environmental | Utah SLC Permit (UTH-0441) Still in Pinnacle's Name — 2.5 Years Post-Acquisition | MEDIUM-HIGH | environmental-permit-schedule.docx §2.2; real-property-lease-schedule.docx §4.1; litigation-regulatory-summary.docx §III.C | Utah hazardous waste transfer station permit UTH-0441 (SLC facility) remains in Pinnacle Waste Solutions, LLC name since March 2022 acquisition. Transfer application pending but not completed. Utah Admin Code R315-3 requires Division approval before ownership/control changes become effective. Sycamore acquisition adds another change-of-control layer. Ogden permit (UTH-0587) was successfully transferred in June 2022 — SLC transfer is the outlier. | Regulatory/operational risk; potential enforcement action | Reasonably Possible | N/A | Open | Accelerate Utah permit transfer to completion before closing. Obtain written confirmation from Utah Division of Waste Management. Make permit transfer a closing condition. | Environmental Counsel / Regulatory | Pre-Closing | Ogden permit transferred successfully — SLC should follow same process.
RF-12 | Debt / Change-of-Control | Bank EBITDA ($18.4M) vs. Management EBITDA ($22.8M) — True Leverage 2.10x Not 1.70x | MEDIUM-HIGH | credit-agreement-summary.docx §4; CIM §XII.B; qoe-data-request-response.xlsx (EBITDA Bridge) | Credit agreement Consolidated EBITDA = $18.4M (expressly excludes all five management add-back categories). Management EBITDA = $22.8M. Bank leverage ratio = 2.10x ($38.7M / $18.4M), not 1.70x as management implies. Covenant maximum = 3.50x. If DOE revenue declines $12.1M with ~30% EBITDA flow-through (~$3.6M), bank EBITDA could fall to ~$14.8M, implying leverage of 2.61x — still within covenant but with reduced headroom. | Covenant headroom risk in downside scenario | Reasonably Possible (downside scenario) | N/A | Monitoring | Model covenant compliance under DOE downside scenario. Confirm no historical covenant breaches. Ensure new credit facility has appropriate covenant structure. | Finance / Legal | Pre-Signing | Discrepancy is 24% — material for covenant analysis.
RF-15 | Customer / Contract | Change-of-Control Provisions in 8 of Top 20 Customer Contracts — $30M+ Revenue at Risk | MEDIUM-HIGH | customer-contract-summary.xlsx (Top 20 Customers tab; Customer Concentration Summary tab) | 8 of top 20 contracts contain assignment/CoC/notification provisions: DOE (non-assignable; novation may be required), Intermountain Health (consent required), Rocky Mountain Pipeline (consent + 30-day notification), Colorado DOT (prior written consent), Utah DEQ (state termination right), Bridger Valley Ranches (mutual consent), Frontier E&P (consent + 30-day notification), Teton Steel (mutual consent). Combined revenue: ~$30M+. | $30M+ revenue at risk from contract termination or renegotiation | Reasonably Possible | N/A | Open | Map all consent requirements. Begin consent solicitation immediately. Make receipt of material consents a closing condition. | Legal / Business Development | Pre-Closing | Customers may use CoC as leverage to renegotiate pricing.
RF-21 | Human Capital | NLRB Unionization Petition — 62 Field Technicians; Not Disclosed in CIM | MEDIUM-HIGH | employee-benefits-summary.docx §7 (footnote); CIM §VII.A | Teamsters Local 455 filed NLRB election petition November 4, 2024 covering 62 field technicians at Grand Junction and Casper facilities. Not disclosed in CIM (which affirmatively states workforce is 'entirely non-unionized'). Disclosed only in a footnote to the benefits summary. 62 employees = ~13% of workforce at two primary facilities. If union election succeeds: increased labor costs, reduced operational flexibility, potential work stoppages. Credit agreement Event of Default if labor dispute exceeds 10 business days. | Labor cost increase; operational risk; potential Event of Default | Reasonably Possible | N/A | Open | Obtain full briefing on NLRB petition, response strategy, and election timeline. Assess likelihood of union victory and cost impact. Qualify CIM representation in SPA disclosure schedules. | HR / Labor Counsel | Immediate | CIM misrepresentation risk — affirmative statement of non-union status is now inaccurate.
RF-05 | Financial / QoE | Revenue Deceleration (11.1% FY2024) and Customer List Inconsistency Between CIM and QoE | MEDIUM | CIM §VI.A; qoe-data-request-response.xlsx (Revenue by Customer tab); customer-contract-summary.xlsx | Revenue growth decelerated from 19.0% (FY2022) to 17.2% (FY2023) to 11.1% (FY2024). QoE Revenue tab lists different customer names than CIM (e.g., QoE #3 = 'Western Slope Energy Partners' $8.9M vs. CIM #3 = 'Western Slope Municipal Water District' $9.8M). These discrepancies suggest different time periods, customer reclassifications, or data inconsistencies requiring reconciliation. | Valuation basis uncertainty; potential revenue overstatement | Reasonably Possible | N/A | Open | Reconcile customer lists between CIM and QoE data. Obtain organic vs. acquired revenue bridge for each fiscal year. | Bridgewater Forsyth | Pre-Signing | Data inconsistency undermines confidence in financial reporting.
RF-10 | Environmental | Asbestos Abatement — Uninsured Pre-2015 Tail Liability; 2 Open WC Claims | MEDIUM | litigation-regulatory-summary.docx §VI.B; insurance-program-summary.docx §2, §4; qoe-data-request-response.xlsx (Service Line Detail tab) | RES operated asbestos abatement 2012–2023 at ~145 sites across CO, UT, WY. Current PLL policy retroactive date = January 1, 2015 — work from 2012–2014 is uninsured. CGL policy has blanket asbestos exclusion; no tail coverage procured. QoE Service Line Detail discloses 2 open WC claims from former asbestos employees alleging occupational respiratory exposure. Cumulative asbestos revenue FY2012–FY2023: ~$31.2M. Long latency of asbestos disease (20–50 years). | Unquantifiable long-tail; 2 open WC claims | Remote (per management) | $0 | Monitoring | Obtain legal opinion on pre-2015 exposure scope. Consider requiring sellers to procure asbestos tail policy or establish dedicated escrow. Negotiate extended survival period for asbestos indemnification. | Legal / Insurance Counsel | Pre-Signing | Management assessment of 'Remote' may be optimistic given 11-year operating history.
RF-13 | Debt / Change-of-Control | Derek Calloway Key-Man Covenant in Credit Agreement — Event of Default if Departed | MEDIUM | credit-agreement-summary.docx §7 (Negative Covenants); §10 (Events of Default) | Credit agreement requires Derek Calloway to remain as CEO and devote substantially full-time attention to the business. Departure without Lender-approved successor = Event of Default (no cure period). Must be addressed in payoff/refinancing. Post-closing, if Buyer intends to replace Calloway, new credit facility must not contain similar provision or transition must be carefully managed. | Event of Default risk if not addressed in payoff | Remote (payoff planned) | N/A | In Progress | Confirm payoff letter releases all key-man provisions. Evaluate post-closing management continuity plans. | Legal / Finance | Pre-Closing | Addressed by planned credit facility payoff at closing.
RF-16 | Customer / Contract | CMMC ($14.5M) — No Minimum Volume Commitments; 60-Day Termination for Convenience | MEDIUM | customer-contract-summary.xlsx (Top 20 Customers tab); CIM §VI.D | Consolidated Mining & Minerals Corp. ($14.5M, 11.4% of revenue) governed by MSA with no guaranteed minimum volume commitments and 60-day termination for convenience. Relationship since 2014 with consistent growth, but no contractual volume protection. Combined with DOE ceiling risk, top 2 customers (30.6% of revenue) have meaningful near-term revenue uncertainty. | $14.5M revenue at risk with 60-day notice | Remote (long-standing relationship) | N/A | Monitoring | Assess depth of CMMC relationship and competitive threats. Consider negotiating longer-term contract with minimum commitments pre-closing. | Business Development / Legal | Pre-Closing | Standard commercial MSA terms but significant revenue concentration.
RF-17 | Customer / Contract | Intermountain Health Systems ($7.1M) — Renewal Decision Pending February 2025 | MEDIUM | customer-contract-summary.xlsx (Top 20 Customers tab) | Intermountain Health Systems contract ($7.1M, 5.6% of revenue) expires June 30, 2025. 2-year renewal option requires 120-day advance notice — renewal decision due ~February 28, 2025, coinciding with target signing date. Contract also requires prior written consent for assignment and 60-day advance notice for change-of-control. | $7.1M revenue at risk if renewal not exercised | Reasonably Possible | N/A | Open | Confirm renewal status before signing. Make renewal (or acceptable replacement revenue) a closing condition or purchase price adjustment trigger. | Business Development / Legal | Pre-Signing | Renewal decision timing coincides with target signing date.
RF-22 | Human Capital | Single-Trigger CoC Severance — $2.625M Certain at Closing; Trigger Structure Inconsistency | MEDIUM | employment-agreements-summary.docx §8; qoe-data-request-response.xlsx (Executive Compensation tab) | CEO and COO employment agreements have single-trigger CoC severance: $1.3125M each = $2.625M total, payable within 30 days of closing regardless of post-closing employment. LOI Transaction Expenses definition does not clearly address these payments. QoE Executive Compensation tab indicates all 5 executives have single-trigger provisions, while Employment Agreements Summary describes CFO, VP Ops, VP BD as double-trigger — inconsistency requires resolution. | $2.625M certain closing cost; up to $1.15M contingent | Certain (CEO/COO); Contingent (others) | N/A | Open | Confirm trigger structure for all 5 executives. Ensure SPA explicitly addresses CoC severance in purchase price mechanics. Budget $2.625M as certain closing cost. | Legal / HR | Pre-Signing | Inconsistency between Employment Agreements Summary and QoE tab must be resolved.
RF-23 | Insurance / Liability | Ramirez Personal Injury Claim ($4.8M) — Insurer Reservation of Rights; Coverage Uncertain | MEDIUM | litigation-regulatory-summary.docx §II.B; insurance-program-summary.docx §4, §7 | Ramirez v. RES (D. Wyo. 2:24-cv-00187) seeks $4.8M for alleged VOC/heavy metal exposure at Sheridan, WY remediation site. Insurer issued reservation of rights letter September 19, 2024 — coverage not confirmed. If claim falls under PLL policy's gradual contamination exclusion (conditions not reported within 72 hours), coverage could be denied. Management's estimated exposure of $500K–$1.5M assumes coverage; uninsured exposure could be full $4.8M. No accrual recorded. Trial date February 2026. | $500K–$4.8M (depending on coverage determination) | Reasonably Possible | $0 accrued | Open | Obtain reservation of rights letter and assess coverage position. Ensure SPA indemnification covers full uninsured exposure. Consider requiring reserve or escrow. | Legal / Insurance Counsel | Pre-Signing | Coverage determination is critical to quantifying net exposure.
RF-19 | Real Property | Pueblo Storage Yard Lease Expiring April 30, 2025 — Coincides with Target Closing Date | LOW-MEDIUM | real-property-lease-schedule.docx §4.4; §5 | Pueblo Storage Yard lease (Arkansas Valley Land Co.) expires April 30, 2025 — same date as target closing. Renewal negotiations underway but not complete. Facility used for equipment and vehicle storage. Failure to renew could require relocation of equipment, incurring unbudgeted costs. | Relocation costs (modest) | Reasonably Possible | N/A | In Progress | Confirm renewal status before closing. Include lease renewal as closing condition or obtain representation that facility is not material to operations. | Real Estate / Operations | Pre-Closing | Timing coincidence with closing date creates unnecessary uncertainty.
RF-20 | Real Property | Grand Junction Property Appraisal Stale (March 2022) — Environmental Conditions Not Reflected | LOW | real-property-lease-schedule.docx §2.1; phase-ii-esa-executive-summary.docx | Grand Junction owned property last appraised at $6.8M in March 2022 — nearly 3 years ago. Environmental contamination (petroleum hydrocarbons and chlorinated solvents) identified in 2019 Phase II ESA may not be reflected in appraised value. Property secures bank's first-priority mortgage lien. Actual market value may be materially lower than $6.8M after accounting for remediation obligations. | Property value uncertainty; potential overstatement | Reasonably Possible | N/A | Open | Commission updated appraisal accounting for environmental conditions. Ensure SPA property representations are appropriately qualified. | Real Estate / Environmental | Pre-Closing | Lower priority given planned credit facility payoff at closing.

## Executive Dashboard
PROJECT RIDGELINE — EXECUTIVE RED FLAG DASHBOARD
Ridgeline Environmental Services, Inc. ¦ Sycamore Capital Partners, LP ¦ December 2024 ¦ CONFIDENTIAL
SEVERITY SUMMARY
CRITICAL | HIGH | MEDIUM-HIGH | MEDIUM | LOW-MEDIUM | LOW
1 | 5 | 6 | 7 | 1 | 1
RED FLAGS BY CATEGORY
Category | # Red Flags | Highest Severity | Key Risk | Est. Max Exposure
Financial / QoE | 3 | HIGH | EBITDA discrepancy ($1M gap); $5.4M aggressive add-backs; 27% reported EBITDA decline; $9.8M fleet capex backlog | $50M+ EV impact if add-backs disallowed
Environmental | 5 | HIGH | Stale Phase II ESA with unresolved contamination & vapor intrusion; active CDPHE enforcement; expired WY permit; SLC permit in Pinnacle name; asbestos tail | $2.6M–$10M+ remediation; $200K–$1.16M penalty
Debt / Change-of-Control | 3 | HIGH | Mandatory $39.2M+ credit facility prepayment within 5 business days; bank EBITDA 24% below management EBITDA; key-man covenant | $39.2–39.3M (known closing cost)
Customer / Contract | 4 | CRITICAL | DOE IDIQ ceiling exhaustion ($12.1M FY2025 headwind); CoC provisions in 8 contracts; CMMC 60-day termination; Intermountain renewal pending | $12.1M+ revenue headwind; $30M+ at risk
Real Property | 3 | HIGH | SLC lease dual consent failure ($16.2M revenue at risk); Pueblo lease expiring at closing; stale Grand Junction appraisal | $16.2M revenue at risk; relocation costs
Human Capital | 2 | MEDIUM-HIGH | NLRB unionization petition (62 employees, not in CIM); $2.625M certain single-trigger CoC severance at closing | $2.625M certain + $1.15M contingent
Insurance / Liability | 1 | MEDIUM | Ramirez personal injury claim ($4.8M) with insurer reservation of rights — coverage uncertain | $500K–$4.8M (coverage-dependent)
TOP 3 CRITICAL ISSUES REQUIRING IMMEDIATE ACTION
# | RF # | Issue | Finding | Required Action | Exposure
1 | RF-14 | DOE IDIQ Ceiling Exhaustion | Largest customer (19.2% of revenue) projected to exhaust $45M contract ceiling by April–May 2025. Potential $12.1M FY2025 revenue headwind not reflected in valuation. Contract non-assignable without CO consent. | Engage DOE Contracting Officer immediately. Adjust valuation model. Make DOE continuity a closing condition. | $12.1M revenue headwind; $15–25M EV impact
2 | RF-01/02 | EBITDA Discrepancy & Aggressive Add-Backs | $1.0M unexplained gap between CIM ($22.8M) and QoE data room ($23.8M). $5.4M in add-backs include non-standard items (litigation receipt, owner comp normalization). Bank EBITDA = $18.4M — 19% below management figure. | Demand written reconciliation before signing. Independently validate all add-backs. Confirm post-closing founder compensation. | $8–9M EV impact per $1M EBITDA at 8–9x
3 | RF-18 | Salt Lake City Lease — Dual Consent Failure | SLC lease consent requested April 2022 — no response after 32 months. Sycamore acquisition = second CoC event. Landlord sent inquiry letter November 2024. Facility serves $16.2M revenue and operates under permit still in Pinnacle's name. | Obtain landlord consent immediately. Non-negotiable closing condition. Engage Wasatch Industrial Properties directly. | $16.2M revenue at risk; lease termination risk
INDICATIVE VALUATION IMPACT SUMMARY
Item | Management Basis | Adjusted / Risk-Adjusted Basis | Adjustment | Notes
Adjusted EBITDA (Management) | $22.8M | $18.4M–$21.0M (QoE-validated) | ($1.8M)–($4.4M) | Depends on QoE outcome; bank EBITDA = $18.4M
Enterprise Value (8.0x–9.0x) | $182M–$205M | $147M–$189M (risk-adjusted) | ($16M)–($58M) | Reflects EBITDA adjustment at midpoint multiple
DOE Revenue Headwind (FY2025) | Not reflected | ($12.1M) revenue; ~($3.6M) EBITDA | ($29M)–($32M) EV | At 8–9x on $3.6M EBITDA flow-through
Fleet Capex Backlog | $4.0–4.5M/yr normalized | $7.0–7.5M/yr true normalized | ($3.0M/yr) | Reduces free cash flow; affects valuation
Credit Facility Prepayment | $38.7M (principal) | $39.2–39.3M (incl. premium) | ($263K+) | Prepayment premium + breakage costs
CoC Severance (certain) | Not in LOI mechanics | $2.625M certain at closing | ($2.625M) | CEO + COO single-trigger; payable within 30 days
Environmental Remediation Reserve | $2.2M accrued (2019 basis) | $3M–$10M+ (updated estimate) | ($0.8M)–($7.8M) | Requires updated Phase II ESA
CDPHE Penalty Exposure | $0 accrued | $200K–$1.16M | ($200K)–($1.16M) | Probable; settlement expected Q1 2025
Ramirez Claim (uninsured portion) | $0 accrued | $0–$4.8M (coverage-dependent) | ($0)–($4.8M) | Reservation of rights; coverage uncertain

## Action Item Tracker
PROJECT RIDGELINE — DILIGENCE ACTION ITEM TRACKER
Ridgeline Environmental Services, Inc. ¦ Sycamore Capital Partners, LP ¦ December 2024 ¦ CONFIDENTIAL
Priority | RF # | Action Item | Category | Owner | Due Date | Status | Closing Condition? | Notes
1 — CRITICAL | RF-14 | Engage DOE Contracting Officer regarding IDIQ ceiling modification; obtain written assessment of ceiling increase likelihood and timeline | Customer/Contract | Deal Team / Legal | Immediate | Open | YES | Revenue sustainability of largest customer at stake
2 — CRITICAL | RF-01 | Demand written reconciliation of $1.0M EBITDA discrepancy between CIM ($22.8M) and QoE data room ($23.8M) | Financial/QoE | CFO / Bridgewater Forsyth | Immediate | Open | YES | Cannot finalize valuation without resolution
3 — CRITICAL | RF-18 | Initiate direct engagement with Wasatch Industrial Properties to obtain landlord consent to (a) 2022 Pinnacle-to-RES assignment and (b) Sycamore acquisition | Real Property | Legal / Real Estate | Immediate | Open | YES | Non-negotiable closing condition; $16.2M revenue at risk
4 — HIGH | RF-06 | Commission updated Phase II ESA and vapor intrusion assessment at Grand Junction headquarters facility | Environmental | Environmental Counsel / Elkhorn | Immediate | Open | YES | 2019 ESA explicitly warns against reliance in property transactions without update
5 — HIGH | RF-21 | Obtain full briefing on NLRB Teamsters petition (62 employees); assess election timeline, response strategy, and cost impact of potential CBA | Human Capital | HR / Labor Counsel | Immediate | Open | NO | CIM misrepresentation risk — affirmative non-union statement now inaccurate
6 — HIGH | RF-02 | Independently validate all five EBITDA add-backs; confirm post-closing founder compensation arrangements; assess recurrence of ERP and integration costs | Financial/QoE | Bridgewater Forsyth | Pre-Signing | Open | YES | Owner comp normalization is most sensitive — must confirm post-closing terms
7 — HIGH | RF-11 | Arrange committed refinancing of $38.7M credit facility; confirm prepayment premium calculation based on actual closing date; ensure SPA Net Debt definition includes premium and breakage | Debt/CoC | Finance / Legal | Pre-Signing | In Progress | YES | Prepayment is certain; premium must be precisely quantified
8 — HIGH | RF-07 | Obtain CDPHE's current settlement position on Docket CDPHE-HW-2024-0093; confirm no permit modification or suspension risk; negotiate specific indemnity escrow | Environmental | Environmental Counsel | Pre-Signing | Open | YES | LOI §5.5 specifically calls out this matter for special indemnification
9 — HIGH | RF-04 | Commission independent fleet condition assessment; adjust normalized maintenance capex in valuation model; negotiate purchase price reduction or capex true-up mechanism | Financial/QoE | Operations / Technical Advisor | Pre-Signing | Open | NO | $9.8M deferred replacement backlog; $3M+/yr capex understatement
10 — HIGH | RF-15 | Map all change-of-control consent requirements across top 20 customer contracts; begin consent solicitation process; make receipt of material consents a closing condition | Customer/Contract | Legal / Business Development | Pre-Signing | Open | YES | 8 contracts with CoC provisions; $30M+ revenue at risk
11 — MED-HIGH | RF-09 | Accelerate Utah permit transfer (UTH-0441) from Pinnacle to RES; obtain written confirmation from Utah Division of Waste Management; make transfer a closing condition | Environmental | Environmental Counsel / Regulatory | Pre-Closing | Open | YES | Ogden permit transferred successfully in June 2022 — SLC should follow same process
13 — MED-HIGH | RF-17 | Confirm Intermountain Health Systems renewal decision (due ~February 28, 2025); make renewal a closing condition or purchase price adjustment trigger | Customer/Contract | Business Development / Legal | Pre-Signing | Open | YES | Renewal decision timing coincides with target signing date
14 — MED-HIGH | RF-22 | Confirm trigger structure (single vs. double) for all 5 executive employment agreements; ensure SPA explicitly addresses CoC severance in purchase price mechanics; budget $2.625M as certain closing cost | Human Capital | Legal / HR | Pre-Signing | Open | NO | Inconsistency between Employment Agreements Summary and QoE tab must be resolved
15 — MED-HIGH | RF-12 | Model covenant compliance under DOE downside scenario; confirm no historical covenant breaches; ensure new credit facility has appropriate covenant structure | Debt/CoC | Finance / Legal | Pre-Signing | Monitoring | NO | Bank leverage 2.10x vs. management-implied 1.70x — 24% discrepancy
16 — MEDIUM | RF-23 | Obtain Ramirez reservation of rights letter; assess coverage position under CGL and PLL policies; ensure SPA indemnification covers full uninsured exposure | Insurance/Liability | Legal / Insurance Counsel | Pre-Signing | Open | NO | Coverage determination critical to quantifying net exposure
17 — MEDIUM | RF-10 | Obtain legal opinion on scope of pre-2015 asbestos exposure (2012–2014 operations); consider requiring sellers to procure asbestos tail policy or establish dedicated escrow | Environmental | Legal / Insurance Counsel | Pre-Signing | Open | NO | Management assessment of 'Remote' may be optimistic given 11-year operating history
18 — MEDIUM | RF-16 | Assess depth of CMMC relationship and competitive threats; consider negotiating longer-term contract with minimum volume commitments pre-closing | Customer/Contract | Business Development / Legal | Pre-Closing | Monitoring | NO | Standard commercial MSA terms but significant revenue concentration ($14.5M)
19 — MEDIUM | RF-13 | Confirm payoff letter releases all key-man provisions (Derek Calloway CEO covenant); evaluate post-closing management continuity plans | Debt/CoC | Legal / Finance | Pre-Closing | In Progress | YES | Addressed by planned credit facility payoff at closing
20 — MEDIUM | RF-05 | Reconcile customer lists between CIM and QoE data room; obtain organic vs. acquired revenue bridge for each fiscal year | Financial/QoE | Bridgewater Forsyth | Pre-Signing | Open | NO | Data inconsistency undermines confidence in financial reporting
21 — LOW-MED | RF-19 | Confirm Pueblo Storage Yard lease renewal status; include lease renewal as closing condition or obtain representation that facility is not material to operations | Real Property | Real Estate / Operations | Pre-Closing | In Progress | NO | Timing coincidence with closing date creates unnecessary uncertainty
22 — LOW | RF-20 | Commission updated appraisal of Grand Junction property accounting for environmental conditions; ensure SPA property representations are appropriately qualified | Real Property | Real Estate / Environmental | Pre-Closing | Open | NO | Lower priority given planned credit facility payoff at closing
23 — HIGH | RF-03 | Obtain detailed FY2023-to-FY2024 EBITDA bridge explaining drivers of 27% reported EBITDA decline; assess whether margin compression is temporary or structural | Financial/QoE | Bridgewater Forsyth | Pre-Signing | Open | NO | Revenue growth with EBITDA decline is a significant quality-of-earnings concern

## Financial Impact Summary
PROJECT RIDGELINE — FINANCIAL IMPACT SUMMARY
Ridgeline Environmental Services, Inc. ¦ Sycamore Capital Partners, LP ¦ December 2024 ¦ CONFIDENTIAL
EBITDA BRIDGE — MANAGEMENT TO RISK-ADJUSTED
Line Item | Amount ($M) | Notes
Management Adjusted EBITDA (CIM) | $22.8M | As presented in CIM; QoE data room shows $23.8M — $1.0M gap unresolved (RF-01)
Less: Litigation settlement add-back (non-standard) | ($1.2M) | Receipt, not a cost — non-standard add-back; should not inflate EBITDA (RF-02)
Less: Owner comp normalization (post-closing uncertain) | ($0.95M) | Assumes founders replaced at $400K each; if founders remain at $875K, add-back evaporates (RF-02)
Less: ERP costs (potentially recurring) | ($0.65M) | Phase 2 ongoing through Q2 FY2025; may not be fully non-recurring (RF-02)
Less: Pinnacle integration (2.5 years post-close) | ($0.80M) | Integration 'substantially complete' yet costs continue — questionable non-recurring classification (RF-02)
Less: Asbestos wind-down (legitimate but tail risk) | ($1.80M) | Legitimate non-recurring; however, asbestos tail liability is uninsured pre-2015 (RF-10)
Bank Covenant EBITDA (Consolidated EBITDA per Credit Agreement) | $18.4M | Operative figure for covenant compliance; expressly excludes all five add-back categories (RF-12)
Less: DOE revenue ceiling exhaustion impact (~30% flow-through) | ($3.6M) | If DOE revenue declines $12.1M in FY2025 with ~30% EBITDA margin (RF-14)
Less: Normalized maintenance capex understatement | ($3.0M) | True normalized maintenance capex ~$7.0–7.5M vs. management's $4.0–4.5M (RF-04)
Risk-Adjusted EBITDA (Downside Scenario) | ~$11.8M | Illustrative downside; actual outcome depends on DOE ceiling modification and QoE findings
ENTERPRISE VALUE BRIDGE
Management EV (8.0x–9.0x × $22.8M) | $182M–$205M | As presented in CIM and LOI
Risk-Adjusted EV (8.0x–9.0x × $18.4M bank EBITDA) | $147M–$166M | Using bank covenant EBITDA as more conservative basis
Risk-Adjusted EV (8.0x–9.0x × $11.8M downside EBITDA) | $94M–$106M | Illustrative downside scenario — not a price recommendation
KNOWN CLOSING COST ADJUSTMENTS
Credit facility mandatory prepayment (principal) | ($38.7M) | Captured in LOI Net Debt adjustment (RF-11)
Term loan prepayment premium (1.0%) | ($0.263M) | Must be added to Net Debt definition in SPA (RF-11)
CEO + COO single-trigger CoC severance | ($2.625M) | Certain at closing; treatment in purchase price mechanics unresolved (RF-22)
CDPHE penalty (management estimate) | ($0.2M)–($0.45M) | Probable; no accrual recorded (RF-07)
Environmental remediation reserve (incremental) | ($0.8M)–($7.8M) | Incremental above $2.2M accrued; requires updated Phase II ESA (RF-06)
Ramirez claim (uninsured portion) | ($0)–($4.8M) | Coverage-dependent; reservation of rights issued (RF-23)